## Blad1
Wonopoly
Items
[5 empty] | Total Estimate: | Day:
| Total Hours Spend: 22,75h |  |  |  | 125.8 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Hours worked:
| item ID | Priority | Backlog Item | Owner | Estimate | / | 8 | 0 | 11.25 | 3.5 | 1.25 | 0 | 5.5 | 2.95 | 1.5 | 1.25 | 7.3 | 2 | 5.65 | 3.8 | 1 | 3 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| V1 Interactable board |  |  |  | 22.5 | Day: 0: Deadline: 1 mei
V0.1 Planning | bar: Day: 0
| 1 | HIGH | Vision document | LF, JK | 2 | Day: 0: 0; Day: 1: 2; Day: 2: 0; Day: 3: 1
| 2 | HIGH | UML | LF, JK | 2 | Day: 0: 0; Day: 1: 3; Day: 2: 0; Day: 3: 1.5
| 3 | HIGH | Backlog | LF, JK | 1 | Day: 0: 0; Day: 1: 3; Day: 2: 0; Day: 3: 1.5
| 4 | MEDIUM | GUI's | LF | 1 | Day: 0: 0; Day: 3: 1
V0.2 Board | bar: Day: 0
| 4 | HIGH | Project setup | JK | 0.5 | Day: 0: 0; Day: 3: 0.25
| 5 | MEDIUM | MainMenuWindow | JK | 1 | Day: 0: 0; Day: 3: 1
| 6 | HIGH | GameWindow | LF | 1 | Day: 0: 0; Day: 3: 2
| 7 | HIGH | Game | JK | 0.5 | Day: 0: 0; Day: 3: 0.5
| 8 | HIGH | Board | LF | 0.5 | Day: 0: 0; Day: 3: 0.5
| 9 | HIGH | BoardGraphicsScene | JK | 3 | Day: 0: 0; Day: 3: 0.25; Day: 4: 0; Day: 5: 1
| 10 | HIGH | Square | LF | 0.5 | Day: 0: 0; Day: 3: 0.5
| 11 | HIGH | SquareGraphicsItem | JK | 3 | Day: 0: 0; Day: 3: 0.25; Day: 4: 0; Day: 5: 0.25
V0.3 Player movement | bar: Day: 0
| 12 | HIGH | Player | LF | 0.5 | Day: 0: 0; Day: 4: 0.5; Day: 5: 0; Day: 6: 0; Day: 7: 1
| 13 | HIGH | PlayerGraphicsItem | LF | 2 | Day: 0: 0; Day: 4: 0.5; Day: 5: 0; Day: 6: 0; Day: 7: 3
| 14 | HIGH | Dice | JK | 1 | Day: 0: 0; Day: 3: 0.5; Day: 4: 0.5
| 15 | HIGH | DiceGraphicsScene | JK | 2 | Day: 0: 0; Day: 3: 0.5; Day: 4: 1.5
| 16 | HIGH | Player::Move | LF | 0.5 | Day: 0: 0; Day: 4: 0.5
| 17 | HIGH | Game::Move | LF | 0.5 | Day: 0: 0; Day: 7: 0.5
| 18 | HIGH | Update UML | LF | 1 | Day: 0: 0; Day: 7: 1
| V2 Owning properties |  |  |  | 27.1 | Day: 0: Deadline: 8 mei
| V1.1 Player properties |  |  |  |  | Day: 0: Deadline: 4 mei
| 18 | HIGH | Card | JK | 0.5 | Day: 0: 0; Day: 8: 0.1
| 19 | HIGH | CardList | JK | 0.5 | Day: 0: 0; Day: 8: 0.5
| 20 | LOW | CardWidget | LF | 3 | Day: 0: 0; Day: 8: 1.5
| 21 | HIGH | Money | JK | 0.1 | Day: 0: 0; Day: 8: 0.1
| 22 | HIGH | Balance | JK | 0.5 | Day: 0: 0; Day: 8: 0.75; Day: 9: 0; Day: 10: 0.25
| 23 | MEDIUM | Bankruptcy | JK | 1 | Day: 0: 0; Day: 10: 1
| 24 | MEDIUM | Create a player list + show current player | LF | 4 | Day: 0: 0; Day: 9: 1.5; Day: 10: 0; Day: 11: 1.5
V1.2 Streets | bar: Day: 0
| 25 | HIGH | StartSquare | LF | 0.5 | Day: 0: 0; Day: 11: 0.5
| 26 | HIGH | StreetSquare | JK | 2 | Day: 0: 0; Day: 13: 0.5
| 27 | HIGH | StreetCard | JK | 1 | Day: 0: 0; Day: 13: 1.25
| 28 | HIGH | StreetSquare::doEffect | JK | 2 | Day: 0: 0; Day: 13: 0.75
| 29 | LOW | SquareGraphicsItem textures | JK | 0.5 | Day: 0: 0; Day: 13: 0.5
V1.3 Buying | bar: Day: 0
| 30 | HIGH | PurchaseWindow | LF | 3 | Day: 0: 0; Day: 11: 3
| 31 | HIGH | AuctionWindow | LF | 3 | Day: 0: 0; Day: 11: 2; Day: 12: 2; Day: 13: 1
| 32 | HIGH | StreetSquare::doEffect aanpassen | LF | 1 | Day: 0: 0; Day: 13: 1
V1.4 Stations | bar: Day: 0
| 33 | HIGH | StationSquare | JK | 0.5 | Day: 0: 0; Day: 13: 0.1
| 34 | HIGH | StationCard | JK | 0.5 | Day: 0: 0; Day: 13: 0.1
| 35 | HIGH | StationSquare::doEffect | JK | 1 | Day: 0: 0; Day: 13: 0.25
V1.5 Company | bar: Day: 0
| 36 | HIGH | CompanySquare | LF | 0.5 | Day: 0: 0; Day: 11: 0.1
| 37 | HIGH | CompanyCard | LF | 0.5 | Day: 0: 0; Day: 14: 1
| 38 | HIGH | CompanySquare::doEffect | LF, JK | 1.5 | Day: 0: 0; Day: 11: 0.1; Day: 12: 0; Day: 13: 0.1; Day: 14: 2; Day: 15: 1
| 39 | HIGH | Refactoring | LF, JK | 4 | Day: 0: 0; Day: 16: 1; Day: 17: 2
| 40 | HIGH | Update UML | LF | 2 | Day: 0: 0; Day: 16: 2; Day: 17: 5.5
| V3 Other square functionality |  |  |  | 7.1 | Day: 0: Deadline: 10 mei
V2.1 Simple squares | bar: Day: 0
| 41 | HIGH | IncomeTaxSquare | LF | 0.5 | Day: 0: 0
| 42 | HIGH | FreeSquare | LF | 0.2 | Day: 0: 0; Day: 11: 0.1
| 43 | MEDIUM | ChanceSquare | JK | 0.2 | Day: 0: 0; Day: 14: 0.2
| 44 | MEDIUM | CommunityChestSquare | JK | 0.2 | Day: 0: 0; Day: 14: 0.1
V2.2 Jail | bar: Day: 0
| 45 | HIGH | Jail | LF | 2 | Day: 0: 0
| 46 | HIGH | JailSquare | JK | 1 | Day: 0: 0; Day: 14: 0.25
| 47 | HIGH | PoliceSquare | JK | 1 | Day: 0: 0; Day: 14: 0.25
| 48 | MEDIUM | Implement Jail into Game | LF | 2 | Day: 0: 0
| V4 Gameloading |  |  |  | 10 | Day: 0: Deadline: 11 mei
| 49 | HIGH | Gameloader (Squares) | LF | 5 | Day: 0: 0
| 50 | HIGH | Gameloader (Cards) | JK | 3 | Day: 0: 0
| 51 | HIGH | Gameloader (Players) | LF | 1 | Day: 0: 0
| 52 | MEDIUM | Gameloader (Jail) | JK | 1 | Day: 0: 0
| V5 Building |  |  |  | 13.1 | Day: 0: Deadline: 15 mei
V4,1 Interactable cards | bar: Day: 0
| 53 | HIGH | CardActions | LF | 1 | Day: 0: 0
| 54 | MEDIUM | CardActionsWindow | JK | 2 | Day: 0: 0
| 55 | MEDIUM | CardListWindow | LF | 3 | Day: 0: 0
| 56 | MEDIUM | PlayerSelectionWindow | JK | 1 | Day: 0: 0
V4,2 Build option | bar: Day: 0
| 57 | HIGH | StreetCard::BuildTier | JK | 0.1 | Day: 0: 0; Day: 13: 0.1
| 58 | HIGH | StreetSet aanpassen | JK | 3
| 59 | HIGH | CardActions building | JK | 3 | Day: 0: 0
| V6 Ohter actions |  |  |  | 16 | Day: 0: Deadline: 19 mei
V5.1 Selling | bar: Day: 0
| 60 | HIGH | CardActions selling | LF | 3 | Day: 0: 0
| 61 | HIGH | CardActions downgrading | LF | 3 | Day: 0: 0
V5,2 Morgage | bar: Day: 0
| 62 | HIGH | CardActions morgage | LF | 3 | Day: 0: 0
V5.3 Trading | bar: Day: 0
| 63 | LOW | Trade | JK | 2 | Day: 0: 0
| 64 | LOW | TradeWindow | JK | 5 | Day: 0: 0
V5.3 Auction Rework | bar: Day: 0
| 65 | HIGH | Rework auctioning | LF | 5 | Day: 0: 0
| V7 Action cards |  |  |  | 18 | Day: 0: Deadline: 21 mei
| 65 | LOW | ChanceSquare | LF | 3 | Day: 0: 0
| 66 | LOW | ChanceCard | LF | 3 | Day: 0: 0
| 67 | LOW | CommunityChestSquare | JK | 3 | Day: 0: 0
| 68 | LOW | CommunityChestCard | JK | 3 | Day: 0: 0
| 69 | LOW | Update Gameloader | LF, JK | 3 | Day: 0: 0
| 70 | LOW | Update CardActions | JK | 3 | Day: 0: 0
| V8 Final |  |  |  | ? | Day: 0: Deadline: 25 mei
V7,1 Polishing | bar: Day: 0
| 71 | HIGH | Debugging | LF, JK | ? | Day: 0: 0
| 72 | LOW | UI Polish | LF | ? | Day: 0: 0
| 73 | LOW | Quality of life | JK | ? | Day: 0: 0
V7,2 Revisioning | bar: Day: 0
| 74 | HIGH | Revision UML | LF | ? | Day: 0: 0
| 75 | HIGH | Refactor code | JK | ? | Day: 0: 0
Total hours remaining:
[6 empty] | 125.8 | 117.8 | 117.8 | 106.55 | 103.05 | 101.8 | 101.8 | 96.3 | 93.35 | 91.85 | 90.6 | 83.3 | 81.3 | 75.65 | 71.85 | 70.85 | 67.85 | 60.35
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
[6 empty] | 125.8 | 121.6067 | 117.4133 | 113.22 | 109.0267 | 104.8333 | 100.64 | 96.4467 | 92.2533 | 88.06 | 83.8667 | 79.6733 | 75.48 | 71.2867 | 67.0933 | 62.9 | 58.7067 | 54.5133 | 50.32 | 46.1267 | 41.9333 | 37.74 | 33.5467 | 29.3533 | 25.16 | 20.9667 | 16.7733 | 12.58 | 8.3867 | 4.1933 | 0
[7 empty] | Verantwoordelijkheden: | [6 empty] | Verantwoordelijke:
[8 empty] | - UML updaten na elke versie | [5 empty] | Liam Froyen
[8 empty] | - Backlog updaten (github) | [5 empty] | Jesse Kavse
[8 empty] | - Voortgangspunten | [5 empty] | Jesse Kavse
[8 empty] | - Deadlines | [5 empty] | Jesse Kavse
[8 empty] | - Uploaden | [5 empty] | Liam Froyen
|  |  | Hours of estimated work per person: | LF | JK | 0: LF, JK; 2: LF; 3: JK; 4: LF, JK
[6 empty] | 2 |  |  |  | 3
|  |  | Total estimated hours of work per person: |  |  | 0: 2; 4: 4.5
|  | LF | 59.7 |  |  | 0: 1; 4: 4.5
|  | JK | 52.6 | 1 | bar: 2
|  | LF, JK | 13.5
|  | TOTAL | 125.8 |  | 0.5 | 3: 0.25
1 | bar: 3
|  |  | Total actual hours of work per person: | 1 |  | 2: 2
|  | LF | 33.7 |  | 0.5 | 3: 0.5
|  | JK | 13.55 | 0.5 |  | 2: 0.5
|  | LF, JK | 18.2 |  | 3 | 3: 1.25
|  | TOTAL | 65.45 | 0.5 |  | 2: 0.5
[5 empty] | 3 | 3: 0.5
|  |  |  | 0.5 |  | 2: 1.5
|  |  |  | 2 |  | 2: 3.5
1 | bar: 3
[5 empty] | 2 | 3: 2
|  |  |  | 0.5 |  | 2: 0.5
|  |  |  | 0.5 |  | 2: 0.5
1 | bar: 2
[5 empty] | 0.5 | 3: 0.1
[5 empty] | 0.5 | 3: 0.5
|  |  |  | 3 |  | 2: 1.5
[5 empty] | 0.1 | 3: 0.1
0.5 | bar: 3
1 | bar: 3
|  |  |  | 4 |  | 2: 3
|  |  |  | 0.5 |  | 2: 0.5
[5 empty] | 2 | 3: 0.5
[5 empty] | 1 | 3: 1.25
[5 empty] | 2 | 3: 0.75
[5 empty] | 0.5 | 3: 0.5
|  |  |  | 3 |  | 2: 3
|  |  |  | 3 |  | 2: 5
1 | bar: 2
[5 empty] | 0.5 | 3: 0.1
[5 empty] | 0.5 | 3: 0.1
[5 empty] | 1 | 3: 0.25
|  |  |  | 0.5 |  | 2: 0.1
0.5 | bar: 2
[6 empty] | 1.5 |  |  |  | 3.2
[6 empty] | 4 |  |  |  | 3
|  |  |  | 2 |  | 2: 7.5
|  |  |  | 0.5 |  | 2: 0
|  |  |  | 0.2 |  | 2: 0.1
[5 empty] | 0.2 | 3: 0.2
[5 empty] | 0.2 | 3: 0.1
|  |  |  | 2 |  | 2: 0
[5 empty] | 1 | 3: 0.25
[5 empty] | 1 | 3: 0.25
|  |  |  | 2 |  | 2: 0
|  |  |  | 5 |  | 2: 0
[5 empty] | 3 | 3: 0
|  |  |  | 1 |  | 2: 0
[5 empty] | 1 | 3: 0
|  |  |  | 1 |  | 2: 0
[5 empty] | 2 | 3: 0
|  |  |  | 3 |  | 2: 0
[5 empty] | 1 | 3: 0
[5 empty] | 0.1 | 3: 0.1
[5 empty] | 3 | 3: 0
[5 empty] | 3 | 3: 0
|  |  |  | 3 |  | 2: 0
|  |  |  | 3 |  | 2: 0
|  |  |  | 3 |  | 2: 0
[5 empty] | 2 | 3: 0
[5 empty] | 5 | 3: 0
|  |  |  | 5 |  | 2: 0
|  |  |  | 3 |  | 2: 0
|  |  |  | 3 |  | 2: 0
[5 empty] | 3 | 3: 0
[5 empty] | 3 | 3: 0
[6 empty] | 3 |  |  |  | 0
[5 empty] | 3 | 3: 0
[6 empty] | ? |  |  |  | 0
|  |  |  | ? |  | 2: 0
[5 empty] | ? | 3: 0
|  |  |  | ? |  | 2: 0
[5 empty] | ? | 3: 0